## Sheet1
Stakeholder engagement assessment matrix
Stakeholders | Unware | Resistant | Neutral | Supportive | Leading | Stakeholder | Communication path
Customer ( Company - foundation - person - ectra…) |  |  |  | C,D |  | customer | Depending on the flexibility of the customer's schedule, I will organize a weekly or biweekly meeting. Keep him informed of any project updates.
sponsor |  |  |  | C | D | Sponsor | Improve your clarity within the parameters of our project. Assure him of his crucial position within the project. Always keep him informed of any modifications as the project progresses.
software team | C |  |  |  | D | Software team | Set up a weekly gathering. Always stay in touch, whether through meetings or other communication channels.
HR team |  | C |  |  | D |  | Encourage them and emphasize their accomplishments.
Quilty team |  | C |  | D |  | HR team | I'll make an effort to persuade them to hire a particular applicant to complete our project's construction. putting together a data sheet or a proposal that details the financial gain for our organization from taking on the job.
suppliers |  |  |  | C,D |  | Store owners | I'll go to their stores and schedule meetings with each of the store managers. giving them the application idea after describing our business and what we do. Moreover, demonstrate to them the value of such an app for them.
store owners (Restaurants - café - ectra…) | C |  |  | D
project manager |  |  | C | D
Communication management plan
Message / Purpose | Responsibility | Audience | Medium | Frequancy / Timing
Project status | PM | Customer | Meeting | Bi-weekly
Team status | PM | Team | Meeting | weekly
Project review | PM | Steering commitie | Meeting | monthly
Audit | QA | PM, team | Meeting | monthly
Audit | QA | PM, team | Meeting | monthly
Project Status report | PM | Customer | E-mail | weekly