## Sheet1
Stakeholder engagement assessment matrix
Stakeholders | Unware | Resistant | Neutral | Supportive | Leading
Customer ( Company - foundation - person - ectra…) |  |  |  | C,D
sponsor |  |  |  | C | D
software team | C |  |  |  | D
HR team |  | C |  |  | D
Quilty team |  | C |  | D
suppliers |  |  |  | C,D
store owners (Restaurants - café - ectra…) | C |  |  | D
project manager |  |  | C | D
Communication management plan
Message / Purpose | Responsibility | Audience | Medium | Frequancy / Timing
Project status | PM | Customer | Meeting | Bi-weekly
Team status | PM | Team | Meeting | weekly
Project review | PM | Steering commitie | Meeting | monthly
Audit | QA | PM, team | Meeting | monthly
Audit | QA | PM, team | Meeting | monthly
Project Status report | PM | Customer | E-mail | weekly