## Sheet1
| Impact | [5 empty] | No. | List of risks | No. | List of opporitunities
Propability | . | Trivial | Minor | Moderate | Major | Extreme | 1 | Security issues. | 1 | Picking the Platform for Mobile App Development.
| Rare |  | Risk 3 |  |  |  | 2 | Choosing the wrong development partner. | 2 | Device Compatibility and Screen Size.
| Unlikely |  |  |  | Risk 6 | Risk 4 | 3 | pandemic | 3 | Getting Traction for the App.
| Moderate |  |  |  | Risk 2 |  | 4 | Neglecting UX and UI. | 4 | Maintaining High Performance.
| likely |  |  | Risk 5 |  |  | 5 | Inadequate features. | 5 | Giving More Value to Customers.
| very likely |  |  |  |  | Risk 1 | 6 | a non trained working team | 6 | The App is a Branding Opportunity.
[7 empty] | No. | List of actions
| Impact | [5 empty] | 1 | conduct a research to find out the implementation that competitors may have implemented
Propability | . | Trivial | Minor | Moderate | Major | Extreme | 2 | At the start up of our project choose wisly which partner fit to our mission
| Rare |  |  | Opp. 5 |  |  | 3 | work remotly plane should be settled
| Unlikely |  | Opp. 2 |  |  | Opp. 6 | 4 | consider a UX/UI, hiring a UX/Ui designer at start up.
| Moderate |  |  | Opp. 1 |  |  | 5 | Try to study other compititor app features well and always improve our app.
| likely |  |  |  | Opp. 3 |  | 6 | Test the ability of working team, considering the life time of the project is it ok to fit with traniee team members or not
| very likely |  | Opp. 4